## Version1.0
Reporter | Assignee | Type | Start Date | Description | End Date | Status | Type | Status
Cường | Hoàng | Task | 2016-12-04 | Tìm hiểu login Facebook, tính năng Share | 14/04/2016 | Open | Improvement | Open
| Hoàng | Task | 15/04/2016 | Game Center | 18/04/2016 | Open | Task | In progress
| Quyên | Task | 2016-11-04 | Tạo địa chỉ email sử dụng chung nguyencuong.hqc@gmail.com nguyenhoang.hqc@gmail.com lequyen.hqc@gmail.com feedback.hqc@gmai.com | 2016-11-04 | Closed |  | Closed
Cường | Quyên | Task | 2016-12-04 | Tạo SVN : https://kemngoc_t7ragon/svn/HQC/ '- user: cuong/hoang/quyen - Mật khẩu: hoangquyencuong | 2016-12-04 | Closed
| Quyên | Task | 2016-12-04 | Xem về cách thức quảng cáo, vị trí gắn, khi nào thì có thể share FB | 13/4/2016 | In progress
Quyên | Cường | Task | 2016-10-04 | Tạo demo game HC Jump theo document đặc tả | 2016-11-04 | Closed
| Cường | Task | 2016-11-04 | Đưa thêm cái component Quảng cáo billboard, banner, video ads | 13/4/2016 | In progress